## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home | View Home | Admin, Manager,User | Display the homepage of the website, so that people can see the website prominently | Hungnb | Updated | iter1 | iter3
2 | List Product | List Product | Admin, Manager,User | Display information of products included in the website | All Member | Updated | iter2 | none
3 | CRUD | CRUD product | Admin,Manage | Edit product information | All Member | Doing | iter3 | none
4 | User Login/Changepass | Common | User | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | All Member | Done | iter4 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | DataBase | None | Create database | hungnb | Done
2 | Home | Home | Design home and generate | Hungnb | Done | II.3 | III.5
3 | Register | Register | Register new account | TuanNA | Done
4 | Login/Logout | Login/Logout | Login and Logout in the web | Manhnv | Done
5 | ChangePassword | Change pass | Change Password óc the account | Datna | Done
6 | Search | Search | Search Information ò product | Hunghm | Done
5
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | List product | Add product | Add new product in list | Hunghm | Done
2 | List product | Delete product | Delete product in database | Manhnv | Done | II.3 | III.5
3 | List product | Update product | Update information of product | TuanNA | Done
4 | View List Favourite | View list | view product in list | Datna | Done
5 | Home | Validate changepass | Create validate of register and changpass | Hungnb | To Do |  |  | fix intern 1
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | List Product | Add colum image in database | Add image of product in database | Hungnb | Done | II.3 | III.5
2 | Home | Create box | create confirmation box in changepass | Hunghm | To Do |  |  | fix intern 2
3 | Home | Details in home fage | insert image and info click image | Datna | To Do | II.1 | III.4
4 | Document | Fix Document and database | Fix document | Manhnv, TuanNA | To Do |  |  | fix intern 2
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document